## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button)
Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name.
Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page.
Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page.
Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name.
Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.)
Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons).
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page.
Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player.
Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message.
Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game.
Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable.
Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories.
Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world.
As a Player I want to be able to move my piece into a single diagonal square forward of its starting position so that I can approach my opponent with that piece. | Given that I drag a piece to a different square the game will register a move
Given that i drag a piece to a valid square it will then make that move
Given that i drag a piece to an invalid space it will not make that move
Given that it is not my turn when I drag one of my piece the board will not let me make a move
Given that I submitted a move I want the piece to stay at the location so that the board will keep record of the game.
Given that I try to move a piece more than one space at a time I shouldn't be allowed to.
As a Player I want to wait for my turn so that I can move my piece. | **Given** That it is my turn **when** I click on a piece **then** I expect the game to allow me to move that piece.
**Given** That it is my turn **when** the opponent clicks their piece **then** they will not be able to move that piece.
**Given** That it is my turn **when** I look at the piece icons above the board **then** I should see that the piece icon representing my piece should be highlighted and the opponents piece icon shouldn't be.
**Given** That it is the opponents turn **when** I look at the piece icons above the board **then** I should see that the piece icon representing my opponents piece should be highlighted and my piece icon shouldn't be.
**Given** That it is my turn **when** I move my piece to an invalid spot and click the submit button **then** I should receive an error message, my piece should return to its original location, and the game should still run as if it is my turn.
**Given** That it is my turn **when** I move a piece on the board and click the Backup button **then** I should see the piece I moved return to its original location and I am able to make a different move.
**Given** That it is my turn and I haven't moved my piece **when** I try to click the resign button **then** I should be able to resign from the game (It should be enabled).
As a Player I want to be able to jump over one of my opponents so that I can take their piece that I jumped over out of the game. | Given that I drag a piece over another when I put the piece down then I expect the game to register a jump move
Given I made a valid jump move then I expect the game to remove piece I jumped
Given that I make an invalid jump the game will not allow me to make that move
As a Player I want to be able to resign from the game so that I do not have to continue playing if I know I am going to lose. | **Given** That it is my turn and I have made a move **when** I try to click the resign button **then** I should not be able to resign from the game (It should be disabled).
**Given** That it is my turn **when** my opponent looks at their controls **then** they will see a disabled resign button.
**Given** that I am a player **when** I resign from a game **then** my opponent should see a message that says that they won because their opponent resigned.
**Given** that I am a player **when** my opponent resigns from a game **then** my buttons on my view should switch to one button that says Exit.
As a Player I want to be able to make a piece I move to the other side of the checkerboard a king piece so that I can move it both forwards and backwards. | **Given** a single piece **when** it reaches the opposite side of the board **then** it should change its type to KING.
**Given** a single piece **when** it reaches the opposite side of the board **then** it should change its icon to two stacked pieces.
**Given** a single piece **when** it becomes a king **then** it should be able to move forward or backward.
**Given** a king piece **when** it tries to jump another piece behind it **then** the King should be able to single jump or multiple jump.
**Given** a king piece **when** it's in the middle of a multiple jump **then** it should be able to jump in any direction it wants.
As a Player I want to be able to jump multiple pieces so that I can get closer to winning the game. | **Given** that another dark space is available **when** I jump one piece and a second is available **then** I expect to be able to jump the next piece.
**Given** that another jump is still available **when** I jump the current piece **then** I expect to be able to chain the next piece or not.
**Given** that a king is doing a multiple jump **when** I try to chain a jump backwards **then** I expect the jump to happen.
**Given** that a standard piece is doing a multiple jump **when** I try to chain a jump backwards **then** I expect the jump won't work.
**Given** that another jump is available **when** the player drops the piece **then** the player expects their turn not to end.
As a Player I want to be able to keep playing a game I left earlier so that I can continue with the same piece placement I had prior. | Given that I have finished a game when I choose to replay a game then I am shown all of the moves taken in the game
Given that I have finished a game when I go back home I expect to see a option to replay the moves from a previous game
Given that I have not finished a game when I am at the home route I am not given the option to see the moves from a game
As a Player I want to be able to know if I have lost or if the other Player has lost so that I know when the game is over. | **Given** that my opponent has captured all of my pieces **when** I lose the game **then** I expect the Controls panel to only show the Exit button.
**Given** that my opponent has captured all of my pieces **when** I lose the game **then** I expect that my opponent and I are unable to make additional moves.
**Given** that my opponent has captured all of my pieces **when** I lose the game **then** I expect a message to appear telling me that my opponent has captured all the pieces.
**Given** that my opponent has captured all of my pieces **when** I lose the game **then** I expect my opponent to see the same game view that I see.
As a player I want to be able to play against an AI so I can play without a second real player | **Given** that I have signed in **when** I look at the players listed online **then** I should always see the AI player
**Given** that I click the AI player **when** I get send to the game **then** I should see that I am playing against an AI
**Given** that I'm playing against an AI **when** I submit my turn **then** the AI should make a valid move following my turn
**Given** that the game ends **when** I try to play with the AI again **then** I should play a new game with them
**Given** that a player is playing against the AI **when** a different player tried to play against the AI **then**they will start playing with a different AI
AS a player I want to be able to click a help button so the game can make a valid move for me | **Given** I am playing a game **when** I look at the info area **then** I should see a Help Button
**Given** that it is my turn **when** I click the help button **then** a valid move should be suggested to me
**Given** that it is not my turn **when** I look at the help button **then** I should be disabled